## P
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Start Time | End Time | status
7 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 |  |  | InProgress_In House
8 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 |  |  | InProgress_In House
9 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 |  |  | InProgress_Outsource
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 |  |  | InProgress_In House
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 1400 |  | 10000 |  |  | InProgress_Outsource
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 |  |  | InProgress_In House
4 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 |  |  | InProgress_In House
5 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 |  |  | InProgress_In House
6 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 |  |  | InProgress_In House
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 |  |  | InProgress_In House
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 |  |  | InProgress_In House
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 |  |  | InProgress_In House
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 10000 |  |  | InProgress_Outsource
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 |  |  | InProgress_In House
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 |  |  | InProgress_In House
13 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 10000 |  |  | InProgress_Outsource
14 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 |  |  | InProgress_In House
15 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 |  |  | InProgress_In House
20 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 |  |  | InProgress_In House
21 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 |  |  | InProgress_In House
22 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 |  |  | InProgress_In House
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C1 | Op4 | In House | M2 | 90 | 2.9 | 10000 |  |  | InProgress_In House
23 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C2 | Op4 | In House | M3 | 90 | 2 | 10000 |  |  | InProgress_In House

## prodet
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Start Time | End Time | status | legend
7 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 2024-08-21 09:00 | 2024-08-21 11:00 | InProgress_In House | C1
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 1333 | C3 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-21 09:00 | 2024-08-21 11:00 | InProgress_In House | C3
13 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 10000 | 2024-08-21 09:00 | 2024-08-30 15:30 | InProgress_Outsource | OutSrc
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 10000 | 2024-08-21 09:00 | 2024-10-23 09:00 | InProgress_Outsource | OutSrc
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 2024-08-21 11:00 | 2024-08-21 12:30 | InProgress_In House | C1
8 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 2024-08-21 11:00 | 2024-08-21 13:00 | InProgress_In House | C2
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 2024-08-21 12:30 | 2024-08-21 14:30 | InProgress_In House | C1
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 1400 |  | 10000 | 2024-08-21 12:30 | 2024-09-26 14:30 | InProgress_Outsource | OutSrc
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 1000 | C3 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-21 13:00 | 2024-08-21 14:30 | InProgress_In House | C3
9 | 2 | Product 2 | 2024-08-21 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 | 2024-08-21 13:00 | 2024-08-29 11:40 | InProgress_Outsource | OutSrc
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 2024-08-21 14:30 | 2024-08-21 16:30 | InProgress_In House | C2
20 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 2024-08-21 14:30 | 2024-08-21 16:30 | InProgress_In House | C1
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 2024-08-21 16:30 | 2024-08-22 10:15 | InProgress_In House | C3
21 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 2024-08-22 10:15 | 2024-08-22 12:15 | InProgress_In House | C2
22 | 6 | Product 6 | 2024-08-21 | 2024-09-03 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 2024-08-22 12:15 | 2024-08-22 14:15 | InProgress_In House | C3
24 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 5667 | C3 | Op4 | In House | M2 | 90 | 2.9 | 10000 | 2024-08-22 12:15 | 2024-08-23 12:45 | InProgress_In House | C3
23 | 7 | Product 7 | 2024-08-21 | 2024-09-03 | 8000 | C5 | Op4 | In House | M3 | 90 | 2 | 10000 | 2024-08-23 12:45 | 2024-08-26 16:45 | InProgress_In House | C5
14 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 2024-08-30 15:30 | 2024-09-02 10:25 | InProgress_In House | C2
15 | 4 | Product 4 | 2024-08-21 | 2024-09-02 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 2024-09-02 10:25 | 2024-09-02 12:55 | InProgress_In House | C3
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 2024-09-26 14:30 | 2024-09-27 09:30 | InProgress_In House | C3
4 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 2024-09-27 09:30 | 2024-09-27 14:00 | InProgress_In House | C4
5 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 2024-09-27 14:00 | 2024-09-27 16:15 | InProgress_In House | C5
6 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 2024-09-27 16:15 | 2024-09-30 10:21 | InProgress_In House | C6
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 | 2024-10-23 09:00 | 2024-10-23 16:30 | InProgress_In House | C2
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 2024-10-23 16:30 | 2024-10-25 10:30 | InProgress_In House | C3

## Machine Utilisation
Machine Number | Daily Utilization
M1 | 0.65625
M2 | 0.37946
M3 | 0.41406

## Product Waiting Time
| Product Name | Average Days | Formatted Time
0 | Product 1 | 6.11 | 6 days 2 hours
1 | Product 2 | 0.08 | 0 days 2 hours
2 | Product 3 | 10.1 | 10 days 2 hours
3 | Product 4 | 1.78 | 1 days 18 hours
4 | Product 5 | 0.23 | 0 days 5 hours
5 | Product 6 | 0.36 | 0 days 8 hours
6 | Product 7 | 0.36 | 0 days 8 hours

## Component Waiting Time
| Components | Average Days | Formatted Time
0 | C1 | 0.08 | 0 days 1 hours
1 | C2 | 3.07 | 3 days 1 hours
2 | C3 | 3.17 | 3 days 4 hours
3 | C4 | 9.02 | 9 days 0 hours
4 | C5 | 5.02 | 5 days 0 hours
5 | C6 | 9.3 | 9 days 7 hours

## Late Products
late | late
late | 4
on time | 3